## Oversight Matrix
Owner's Representative — Project Oversight & Accountability Matrix
Casino / Hospitality Development ¦ Generated 2026-06-23
# | Oversight Area / Category | Sub-Element / Focus Item | Lead Responsibility – Owner PDG | Secondary Responsibility – Owner PDG | Lead Responsibility – DNC Developer | Secondary Responsibility – DNC Developer | Notes / Comments
1 | Governance & Decision Framework | Clear authority matrix (Owner Teams / CM / Designer)
Escalation paths and approval timelines
Executive steering cadence
2 | Budget / Cost Control | GMP vs. Budget forecast
Cost-to-complete and contingency drawdown
Trend logs and forecast accuracy
Cashflow
Lender interface
3 | Schedule Management | Critical path tracking
Milestone adherence
Recovery schedule and plans for slippage
Owner scheduling consultant
4 | Change Management | Change order procedure: determination of need, entitlement, fair and reasonable pricing
CO pipeline (approved vs. pending)
Reason codes / root causes (design gaps, owner changes, unforeseen field conditions)
Cost / schedule impact tracking
Requests: RFI, RFP, COR, CCD
Claims & disputes
5 | Scope Control | Alignment between design intent and construction scope
Prevention of scope creep
Trade scope completeness
6 | Design Coordination & Completion | % design complete (IFC quality)
Coordination issues (MEP clashes, architecture)
Architect / engineer responsiveness
Interface and coordination with developer
Coordination with owner consultants
Pay applications
7 | Construction Quality | QA/QC program effectiveness
Inspection results
NCNs — Non-Conformance Notices
Mockups and finishes (critical for a casino)
8 | Safety Performance | OSHA partnering
Safety culture
Contractors' safety programs
Safety compliance
Safety officer
9 | Labor & Workforce Management | Labor availability (especially skilled trades)
Reporting: monthly manpower reports
Union dynamics (if applicable in Colorado markets)
10 | Procurement & Long Lead Items | Key materials (steel, curtain wall, gaming systems, elevators)
Supply chain risk and delays
Buyout status and savings approach and tracking
11 | Contracts | Developer
Construction Manager
Operator
Specialty vendors / consultants
Legal interface
Negotiations
12 | MEP & Systems Integration | Coordination of mechanical, electrical, plumbing
Co-Gen plant
Specialty systems: gaming, surveillance, IT backbone
Commissioning readiness
13 | Commissioning & Turnover | Systems testing plans
Phased turnover strategy
Owner training and documentation
O&M manuals, warranties
14 | Casino-Specific Systems / Interface | Gaming floor integration
Surveillance & security systems (highly regulated)
Food and beverage; retail
Hotel
15 | Site Logistics & Phasing | Laydown areas and material flow
Urban / site constraints
Sequencing of major trades
16 | Reporting & Transparency | Cost + fee tracking
Accuracy of monthly reports
Schedule, change order / RFI logs
Critical issues
Progress photos
QA/QC
Dashboards (KPIs across cost, schedule, safety)
Independent validation (don't rely solely on CM)
17 | Regulatory & Permitting Compliance | Local / state approvals
Colorado gaming regs
Building permits
Inspections and signoffs
Environmental compliance
18 | Sustainability / ESG (if applicable) | Waste and water management
Mechanical systems
Electrical
Envelope building material selection
19 | Risk Management | Bonding
Insurance
Budget control — contingency
20 | Closeout & Punch List | Deficiency tracking
Warranty management
Readiness for phased opening

## Responsibility & Ownership
Responsibility Framework & Ownership Key
Matrix Responsibility Columns (D–G) — What They Mean
Matrix Column | Party | Definition
D — Lead Responsibility – Owner PDG | Owner PDG | Owner's project team (PDG) holds primary accountability: drives, decides, and owns the outcome.
E — Secondary Responsibility – Owner PDG | Owner PDG | Owner PDG supporting / backup role: reviews, contributes, or covers when the lead is unavailable.
F — Lead Responsibility – DNC Developer | DNC Developer | DNC Developer holds primary accountability for executing and delivering the item.
G — Secondary Responsibility – DNC Developer | DNC Developer | DNC Developer supporting / backup role: assists or steps in behind the developer lead.
Owner PDG — Lean Team Staffing by Oversight Area
PDG Team Member | Primary Domains | Oversight Areas Owned (from Matrix)
Person 1 | Cost, Change Orders, Contracts | 2. Budget / Cost Control 4. Change Management 11. Contracts
Person 2 | Schedule, Procurement, Logistics | 3. Schedule Management 10. Procurement & Long Lead Items 15. Site Logistics & Phasing
Person 3 | Quality, Design, Commissioning | 5. Scope Control 6. Design Coordination & Completion 7. Construction Quality 13. Commissioning & Turnover 20. Closeout & Punch List
Person 4 | Site Operations — General Trades | 8. Safety Performance 9. Labor & Workforce Management
Person 5 | Site Operations — MEP, FA, FP, Security | 12. MEP & Systems Integration 14. Casino-Specific Systems / Interface 18. Sustainability / ESG (if applicable)
Person 6 | Risk, Reporting, Governance | 1. Governance & Decision Framework 16. Reporting & Transparency 17. Regulatory & Permitting Compliance 19. Risk Management
Notes: (1) The 6-person lean team staffs the Owner PDG side (matrix columns D–E). Populate columns F–G with the DNC Developer counterparts. (2) Safety & Labor (8, 9) sit with Site Ops (P4); MEP/Casino systems & ESG (12, 14, 18) with P5. Adjust to match the final org chart.